## Gantt Chart
GANTT CHART - DECENTRALIZED VOTING SYSTEM
PROJECT TITLE |  | Decentralized Voting System
TEAM MEMBERS |  | Aura S. Ali |  | 11182143 | [39 empty] | Progress Bar
|  | Mir Ashiqul Hossain |  | 11201464 | [39 empty] | In progress
|  | Azwad Zarif Khan |  | 11183021 | [39 empty] | Almost done
|  | Sadman Sakib |  | 11183013 | [39 empty] | Completed
|  | Sanjida Hossain |  | 11182089
|  | Ashrafun Nahar Ifty |  | 11182133
SECTION (FROM PAPER) | TASK TITLE | TASK OWNER | Week | PHASE ONE - BEFORE MIDTERMS | [29 empty] | PHASE TWO - POST MIDTERMS
|  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | MIDTERMS |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  |  | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S | T | W | T | F | S
0 | Abstract | Abtahi, Wasi, Farzana and Khaled | 2
1 | Introduction
1.1 | Project Overview | Khaled | 2 | bar: WEEK 2 T to WEEK 3 S
1.2 | Motivation | Khaled | 2 | bar: WEEK 2 T to WEEK 3 S
1.3 | Goals & Objectives | Abtahi | 6 | bar: WEEK 2 T to WEEK 3 S
2 | Background
2.1 | Preliminaries | Abtahi, Wasi, Farzana | 8 | bar: WEEK 2 T to WEEK 3 S
2.2.1 | Similar Applications | Wasi and Khaled | 6 | bar: WEEK 2 T to WEEK 3 S
2.2.2 | Related Research | Abtahi, Wasi, Farzana, Khaled and Jobaer | 6 | bar: WEEK 2 T to WEEK 3 S
2.3 | Gap Analysis | Abtahi | 6 | bar: WEEK 2 T to WEEK 3 S
2.4 | Summary | Farzana | 9 | bar: WEEK 2 T to WEEK 3 S
3 | Design
3.1.1 | Functional & Non-functional Requirements | Wasi, Farzana, Abtahi | 8 | bar: WEEK 2 T to WEEK 5 S; WEEK 7 T to WEEK 7 S
3.1.2 | Context diagram | Abtahi | 8 | bar: WEEK 2 T to WEEK 5 S; WEEK 7 T to WEEK 7 S
3.1.3 | Data Flow Diagram Level 1 | Abtahi | 8 | bar: WEEK 2 T to WEEK 5 S; WEEK 7 T to WEEK 7 S
3.1.4 | UI Design | Khaled | 12 | bar: WEEK 2 T to WEEK 5 S; WEEK 7 T to WEEK 7 S
3.2 | Details, Methodology & Design | Everyone | Next Trim | bar: WEEK 2 T to WEEK 5 S; WEEK 7 T to WEEK 7 S
| Requirement Elicitation | Everyone | 10 | bar: WEEK 2 T to WEEK 5 S; WEEK 7 T to WEEK 7 S
| Data Collection | Khaled, Farzana, Jobaer | 12 | bar: WEEK 2 T to WEEK 5 S; WEEK 7 T to WEEK 7 S
3.3 | Project Plan | Wasi, Farzana, Abtahi | 8 | bar: WEEK 2 T to WEEK 5 S; WEEK 7 T to WEEK 7 S
3.4 | Task Allocation | Wasi, Farzana, Abtahi | 8 | bar: WEEK 2 T to WEEK 5 S; WEEK 7 T to WEEK 7 S
4 | Implementation
4.1 | Environment Setup | Wasi, Khaled, Abtahi | Next Trim | bar: WEEK 9 T to WEEK 12 S
| Creating Model | Wasi, Khaled, Abtahi | Next Trim | bar: WEEK 9 T to WEEK 12 S
4.2 | Testing And Evaluation | Wasi, Khaled, Abtahi | Next Trim | bar: WEEK 9 T to WEEK 12 S
4.3 | Results And Discussion | Everyone | Next Trim | bar: WEEK 9 T to WEEK 12 S
5 | Standards And Design Constraints
5.1 | Compliance with the Standards | Farzana, Wasi | 12
5.2 | Design Constraints | Farzana, Wasi | 12
5.3 | Cost Analysis | Farzana, Wasi, Abtahi | 8
5.4 | Complex Engineering Problems and Activities | Farzana, Wasi, Abtahi | 3
6 | Conclusion
6.1 | Summary | Everyone | Next Trim | bar: WEEK 7 T to WEEK 8 S
6.2 | Limitation | Everyone | Next Trim | bar: WEEK 7 T to WEEK 8 S
6.3 | Future Work | Everyone | Next Trim | bar: WEEK 7 T to WEEK 8 S